## Sheet1
PLAYABLE LINK | http://web.cecs.pdx.edu/~kebu2/Always-Pass-By-Value/SpaceHunt/Index.html
REPOSITORY LINK | https://github.com/kburton501/Always-Pass-By-Value
USER STORY | STATUS (Done-Done, In Progress, Did Not Pass Review, Not Started) | CONTRIBUTORS AND ROLE | FILES
SH-1 Spacecraft Movement | Done-Done | Design: Mike; Code: Mike, Bruh; Tests: Mike | ship.js, draw.js, index.html
SH-2 Game Configuration | Did Not Pass Review - Acceptance Crit 1: Adjustable size of map | Design: Tu, Kelly; Code: Tu, Kelly, Bruh; Tests: Tu, Kelly, Bruh, Mike | Config.js, space.js, artifact.js, index.html
SH-3 Running out of Energy | Done-Done | Design: Jake; Code: Jake; Tests: Kelly | ship.js
SH-4 Running out of Supplies | Done-Done | Design: Jake; Code: Jake; Tests: Kelly | ship.js
SH-05: Placing Celestial Artifacts | Done-Done | Design: Kelly, Bruh; Code: Kelly, Tests: Bruh | space.js, artifact.js, index.html
SH-6 Sensor | Done-Done | Design: Kelly; Code: Kelly; Tests: Bruh | sensor.js, artifact.js
SH-7 Celestial Map | Done-Done | Design: Bruh, Kelly; Code: Bruh; Tests: Mike, Kelly | draw.js, space.js, artifact.js, ship.js, index.html
SH-09 - Nameable Persistent state | Done-Done | Design: Mike; Code: Mike; Tests: Bruh, Mike | saveGame.js, index.html
SH-10:Encountering an Abandoned Freighter | Done-Done | Design: Jake, Tu; Code: Jake; Tests: Bruh | ship.js, draw.js
SH-12: Encountering a Meteor Storm | Done-Done | Design: Bruh, Tu; Code: Bruh, Tu; Tests: Kelly, Tu | ship.js, draw.js
SH-13: Collision with an Asteroid | Done-Done | Design: Bruh; Code: Bruh: Tests: Kelly | ship.js, artifact.js, draw.js
SH-14: Being Boarded by Bad Max | Done-Done | Design: Tu, Kelly; Code: Tu; Tests: Tu, Kelly | ship.js, draw.js
SH-15: Entering orbit | Done-Done | Design: Bruh; Code: Bruh; Tests: Kelly | ship.js, artifact.js, draw.js, index.html
SH-16: Leaving Orbit | Done-Done | Design: Bruh; Code: Bruh; Tests: Kelly | ship.js, artifact.js, draw.js, index.html
SH-17: Landing on a Planet | Done-Done | Design: Bruh; Code: Bruh; Tests: Kelly | ship.js, artifact.js, draw.js, index.html
SH-18: Leaving a Planet | Done-Done | Design: Bruh; Code: Bruh; Tests: Kelly | ship.js, artifact.js, draw.js, index.html